## Coria Burndown Chart Template
SPRINT BURNDOWN CHART
| Backlog Item ID | User Stories / Bugs
|  |  | Initial Estimate | Day 1 | Day 2 | Day 3 | Day 4 | Day 5 | Day 6 | Day 7 | Day 8 | Day 9 | Day 10
| 123456 | Example Product Backlog Item (PBI) Estimated During Sprint Planning | 6 | 1 | 0 | 1 | 0 | 2 | 1 | 1 |  |  |  | Legend
| 123457 | Example Bug Included at the Beginning of Sprint Planning | bar: Day 3
| 123458 | Example PBI Entered After Sprint Planning (On Day 3) | [12 empty] | = | Missing at Start | bar: Day 3
| 123459 | Example Bug Entered After Sprint Planning (On Day 5) | [12 empty] | = | Added to Sprint
| 123460 | Example PBI Entered After Sprint Planning (On Day 6) | [12 empty] | = | Projected Value | bar: Day 6; Day 10
|  | Remaining Effort | 6 | 5 | 5 | 5 | 5 | 3 | 2 | 1 | 1 | 1 | 1
|  | Ideal Trend | 6 | 5.4 | 4.8 | 4.2 | 3.6 | 3 | 2.4 | 1.8 | 1.2 | 0.6 | 0
Did you complete all items in your sprint plan?
No
What is your sprint deliverable? (shippable product(s))
Working login page that stores user accounts and connects to main page.
Did you have any task volatility, and what was the cause?
It took a while to get my accounts to store properly, had to rearrange database. - Yes
What would you do differently knowing what you know now?
I have a better understanding of how to create a databse that works in tandem with creating a user account. I would organize my database to fit my application better the first time around rather than the 4th.
Note on E5: Coria: Effort calculated using Story Points assigned at Sprint Planning - Enter as a positive Integer
Note on G6: Coria: Use a positive number to indicate that the item is complete.
Note on H8: Coria: Use a negative number to indicate that the level of effort just went up during your Sprint.
Note on R8: Coria: If something is missing at the start of Sprint Planning, place this color box in column E to indicate it was added after the start of the Sprint.
Note on J9: Coria: Use a negative number to indicate that the level of effort just went up during your Sprint.
Note on L9: Coria: Use a positive number to indicate that the item is complete.
Note on R9: Coria: Format the cell of the day that a missing item was added to the Sprint with this color and add in an estimate of story points for the item.
Note on K10: Coria: Use a negative number to indicate that your level of effort just went up.
Note on O10: Coria: Use this formatting to indicate that you are projecting a number that is not yet final.
Note on R10: Coria: If you are only partway through a Sprint, but would like to project a completion or perform what-if analysis, use this formatting to indicate something is not yet final.